## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | Use Case Name | User Story Name | Candidate Name | Scrum Team Assigned | Complexity | Risk/ Impact | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | US.101 | manage profile | view profile details,update profile details | smriti pandey | Ganesh Prabu | Average | Low | RD:Business Requirement Doc | [5 empty] | 3 days
2 | 2 | Standard document | High | US.102 | login module | Sign up, Login and Logout for both admin and customer | Ranjith Reddy | Ganesh Prabu | Average | Medium | Admin / Customer needs to login to access their respective curds |  | Admin and Customer |  |  |  | 3 days
3 | 3 | Standard document | High | US.103 | list book | Display books based on popularity, published date and number of orders | Karthik Ganji | Ganesh Prabu | Average | Medium | Customer can access books in a sorted manner based on published date,number of orders and ratings. |  | Customer |  |  |  | Required
4 | 4 | Standard document | High | US.104 | view book | view book details using category | Niharika Sanda | Ganesh Prabu | Average | Low | Customer can view the books based on category they want. |  | customer |  |  |  | 3 days
5 | 5 | Standard document | High | US.105 | shopping cart | Add book,Delete book | Anusha Jilla | Ganesh Prabu | Average | Low | RD:Business Requirement Doc | [5 empty] | 3 days
6 | 6 | Standard document | High | US.106 | place order | addOrder,deleteOrder,updateQuantity | Tanugula Prashanth | Ganesh Prabu | Average | Low | RD:Business Requirement Doc |  | Customer |  |  |  | 3 days
7 | 7 | Standard document | High | US.107 | view order history | Display complete customer orders and details by customerId and email, display order details by orderId | Kavya Koppoju | Ganesh Prabu | Average | Medium | Customer can go through all his previous orders whenever required and can also check the details of a particular order. |  | Customer |  |  |  | 4 days

## SprintBacklog
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
PD_01 | US:001 | 1 | Understanding the work flow and analyzed the dependent variables involved in different modules of the project for individual case studies of the team members. | Karthik | 2020-03-08 | 1 day | 1 day | Completed | 1 day | understood the work flow of the project, and implemented the entity classes with relations.
|  | 2 | implemented RestAPIs and tested their working | Karthik | 2020-04-08 | 1.5days | 1.5days | Completed | 1.5days | Implemented RestAPIs and tested their working using postman
|  | 3 | Implementing Junit Test cases | Karthik | 2020-10-08 | 0.5 day | 0.5 day | Completed | 0.5 day | Implemented junit test cases for each functionality.
|  | 4 | ExcpetionHandling and validations | Karthik | 2020-11-08 | 1 day | 1 day | Completed | 1 day | implemented global level exception handling.
|  | 5 | Html page design, wired frames | Karthik | 2020-12-08 | 1 day | 1 day | Completed | 1 day
|  | 6 | Integrating frontend(Angular) with backend and performed required operations | Karthik | 14/88/2020 | 2 days | 2 days | Completed | 2 days | Implemented the Frontend using angular.
|  | 7 | Implementing the frontend with validations at the required fields. | Karthik | 18/8/2020 | 0.5 day | 0.5 day | Completed | 0.5 day | Applied frontend validations for required fields.
|  | 8 | Integration of angular code. | Karthik | 18/8/2020 | 1.5 days | 1.5 days | Completed | 1.5 days | completed the integration of all the individual case studies.