## User stories
| Main User Story | Sub-Task
1 | List books | Sort books based on published date, popularity and number of orders
Add book to cart
Search for specific book

## karthik
Task No. | Task Name | Estimated Days | Actual Time Taken | Allotted on day | Comments
1 | List Book
1.1 | Book list based on rating, popularity
1.1.1 | Understanding User Requirements and Design Diagrams | 1 |  | Monday
1.1.2 | Entity Creation and understanding relationships using JPA | 1 |  | Tuesday
1.1.3 | Designing spring boot application based on requirements | 1 |  | Monday
1.1.4 | Exception handling and validations | 0.5 |  | Tuesday
1.1.5 | Implementing Junit Test cases | 0.5 |  | Tuesday